NSP Project Status

January 31, 2015

Pursuant to Task Order Five of Master Consulting Agreement # NSP-2, the following is a status update of the project, reporting on key elements of the project progress.

- Status of Contract Deliverables.

  - Stadco has submitted all deliverables required by contract except for the 100% Construction Documents due in March 2015.

  - GWCCA Board of Directors has approved Stadco/HHRM GMP.

- Design/Procurement/Permitting.

  - 360 Architecture, now known as HOK Architects, continues toward completing the 100% CD’s by April 2015 with some approved exceptions on interiors and systems.

  - 100% Construction Documents for the Phase One Parking Deck have been completed.  GWCCA review is underway.

  - Land Disturbance permit for Phase One Parking Deck is awaiting acceptance of a water meter easement by GWCCA. Easement has been delivered to COA. Awaiting COA acceptance.

  - Georgia power has submitted its concept design for the PV roof. Coordination with future billboard is required.

  - Subcontract for IBM for special systems, in excess of $25M, has been approved by GWCCA.

- Budget/Cost Status.

  - GMP between Stadco/HHRM remains unchanged for the NSP.

  - GMP for Phase One Parking is due 2/2/15 from HHRM for review and approval by GSFIC/GWCCA.

  - GWCCA has cost risk on Phase One Parking due to unknown quantity of buried debris, final required lengths of augercast piles, and quantity of required haul off of contaminated soils.

- Schedule Status.

  - Concrete work continues at a rapid pace. Approximately 50% of the Concourse Level One slab is complete and work has begun on the Lower Suite level in the south west corner.

  - Structural steel procurement and fabrication continues on schedule for mid 2015 start.

  - HHRM will adjust traffic on Mangum again in March to install augercast piles along west side of Phase One Deck. HHRM will keep three traffic lanes open.

  - Work  is complete on the Combined Sanitary/Storm retention vault on SW side of project.

  - NSP Project continues on target for a 3/31/17 Substantial Completion.

  - Work on the Phase One Parking Deck has begun and is on schedule for a September 2015 completion.

- Quality Assurance.

  - Work is being carefully inspected and documented for “Non-Conforming Work”. Non-conforming work is being addressed in a reasonable timeframe by contractors and remedial work approved by appropriate inspector (Langan/AMEC).

- Safety.

  - No lost time injuries reported.

- Upcoming Major Activities in Next 30 Days.

  - Continued forming, reinforcing and pouring of elevated slabs around perimeter of NSP bowl.

  - Excavations and foundations for Phase One Parking Deck.

  - Review/approval of GMP for Phase One Parking Deck.

  - Production of 100% Construction Documents for the NSP by March 2015.